## FRA SCC What to include where
FRA Standard Cost Categories for Capital Projects What to include where… |  | NOTE: The SCC cost breakdown is based on a traditional Design Bid Build model. If your project is Design Build, to the best of your ability, separate construction costs from design, administration, testing, etc. Put all construction costs in 10 through 50. Put design, administration, testing, etc. in 80 Professional Services.
10 | Guideway & Track Elements Include rough grading, excavation, finish grading, ballast, concrete base when applicable, drainage structures, rails, connectors, transitional curves, ties, vibration and noise dampening; all construction materials and labor regardless of whom is performing the work; put guideway and track elements associated with yards in SCC 30 Support Facilities; For Aerial sructures, include foundation excavation; guideway structures including caissons, columns, bridges, viaducts, cross-overs, fly-overs. For Built-up Fill, include construction of earthen berms. For Underground cut & cover, include excavation, retaining walls, backfill, underground guideway structure and finishes. For Underground tunnel, include tunneling by means of a tunnel boring machine, drill blasting, mining, and immersed tube tunneling; tunnel structure and finishes. For Retained cut or fill, include excavation, retaining walls, backfill, underground guideway structure and finishes.
20 | Stations, Stops, Terminals, Intermodels Include rough grading, excavation, station structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, station power, lighting, public address/customer information system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc.; include all construction materials and labor regardless of whom is performing the work; put guideway and track associated with stations in SCC 10 Guideway & Track Elements above. For Aerial structures, include station structures including caissons, columns, platforms, superstructures, etc. For Underground stations, include retaining walls, backfill, structure. For Joint Development -- describe in the aspect of your project that is income-producing with a transportation nexus related to a real estate asset in which FRA has an interest. . .Joint development is commercial, residential, industrial, or mixed-use development that enhances the effectiveness of transportation projects.
30 | Support Facilities: Yards, Shops, Admin. Bldgs Include costs for rough grading, excavation, support structures, enclosures, finishes, equipment; mechanical and electrical components including HVAC, ventilation shafts and equipment, facility power, lighting, public address system, safety systems such as fire detection and prevention, security surveillance, access control, life safety systems, etc. Include fueling stations. Include all construction materials and labor regardless of whom is performing the work. Where a support facility shares the structure with a station, its cost may be included with station cost. Except for guideway and track associated with a yard, include all guideway and track costs associated with support facilities in SCC 10 Guideway & Track Elements above.
40 | Sitework & Special Conditions Include all construction materials and labor regardless of whom is performing the work; include project-wide clearing, demolition, fine grading; site utilities. For haz mat, include underground storage tanks, fuel tanks, other hazardous materials and treatments, etc. For 40.060, Pedestrian / bike . . . include sidewalks, paths, plazas, landscape, site and station furniture, site lighting, signage, public artwork, bike facilities, permanent fencing. For 40.080, Temporary Facilities . . . - As a general rule and to the extent possible, appropriately allocate indirect costs among the construction costs in Categories 10 through 50. Where that is not possible, include in 40.08 Temporary Facilities costs for mobilization, demobilization, phasing; time and temporary construction associated with weather (heat, rain, freezing, etc.); temporary power and facilities; temporary construction, easements, and barriers for storm water pollution prevention, temporary access and to mitigate construction impacts; project and construction supervision; general conditions, overhead, profit. - For 40.084, Maintenance of Traffic. . . include costs to successfully handle the complexity of construction within an existing operating railroad environment, including the reroute, shutdown, reschedule, stage, phase, worker-protect, and work-around existing rail traffic; also cost of agreements with and/or compensation to impacted freight or passenger train owners and other third parties. NOTE: Include contractor's general liability and other insurance related to construction such as builder's risk in Cats. 10 - 50, not in SCC 80 Professional Services.
50 | Systems Include all construction materials and labor regardless of whom is performing the work. Include passenger information systems at stations and on vehicles (real time travel information; static maps and schedules). Include equipment to allow communications among vehicles and with central control.
60 | Row, Land, Existing Improvements Include real estate costs and professional services costs associated with real estate. Such professional services costs may include agency staff oversight and administration, real estate and relocation consultants, legal counsel, court expenses, insurance, etc. If the value of right-of-way, land, and existing improvements is to be used as local match to the Federal funding of the project, include it as a cost.
70 | Vehicles Include professional services associated with the vehicle component of the project. These costs may include agency staff oversight and administration, vehicle consultants, design and manufacturing contractors, legal counsel, warranty and insurance costs, etc.
80 | Professional Services These costs apply to SCC 10-50. SCC 80 includes all professional, technical and management services related to the design and construction of fixed infrastructure (SCC 10 - 50) during the planning, preliminary engineering, final design, construction, and start-up phases of the project. This includes planning, environmental work, design, engineering and architectural services; specialty services such as safety or security analyses; value engineering, risk assessment, cost estimating, scheduling, ridership forecasting, operations modeling, before-and-after data gathering and analysis, auditing, legal services, administration and management, etc. by agency staff or outside consultants. Include professional liability insurance and other non-construction insurance on SCC 80.05. Include costs associated with professional services related to real estate and vehicles in SCC 60 and SCC 70 respectively.
90 | Unallocated Contingency Includes unallocated contingency, project reserves. Show allocated contingencies for individual line items on the Main Worksheet.
100 | Finance Charges Include finance charges expected to be paid by the Grantee to fund the project.

## FRA Main Worksheet
F R A M A I N W O R K S H E E T | [9 empty] | Issue Date 5/4/16
Grantee Name | [7 empty] | Today's Date |  | 2014-08-28
Project Name and Location: Rail Project A, Two cities with rural in-between | [7 empty] | Yr of Base Year $ |  | 2014
Current Phase : Final Design, Ready to Procure Construction | [7 empty] | Yr of Revenue Ops |  | 2017
Standard Cost Category |  | Unit | Quantity | Base Year Dollars | [5 empty] | YOE Dollars Total (X000) (from Inflation Worksheet)
|  |  |  | Without Contingency (X000) | Allocated Contingency (X000) | TOTAL (X000) | Unit Cost (X000) | Percent of Construction Cost | Percent of Total Project Cost
10 | Guideway & Track Elements | Lineal Miles of Guideway | 105 | 1520000 | 140000 | 1660000 | 15809.5238 | 68.86% | 52.13% | 1718100
10.010 | Guideway: At-grade exclusive right-of-way | Lineal Miles of Guideway | 100 | 550000 | 50000 | 600000 | 6000
10.020 | Guideway: At-grade semi-exclusive (allows cross-traffic) | Lineal Miles of Guideway |  | 0 |  | 0
10.030 | Guideway: At-grade in mixed traffic | Lineal Miles of Guideway |  | 0 |  | 0
10.040 | Guideway: Aerial structure | Lineal Miles of Guideway |  | 0 |  | 0
10.041 | Bridges | Lineal Miles of Guideway |  | 0 |  | 0
10.042 | Viaduct | Lineal Miles of Guideway |  | 0 |  | 0
10.043 | Other Structure | Lineal Miles of Guideway |  | 0 |  | 0
10.044 | Unspecified | Lineal Miles of Guideway |  | 0 |  | 0
10.050 | Guideway: Built-up fill | Lineal Miles of Guideway |  | 0 |  | 0
10.060 | Guideway: Underground cut & cover | Lineal Miles of Guideway |  | 0 |  | 0
10.061 | Cut & Cover Guideway Soft Soils | Lineal Miles of Guideway |  | 0 |  | 0
10.062 | Cut & Cover Guideway Hard Soils | Lineal Miles of Guideway |  | 0 |  | 0
10.063 | Cut & Cover Guideway Vent Soft Soils | Lineal Miles of Guideway |  | 0 |  | 0
10.064 | Cut & Cover Guideway Vent Hard Soils | Lineal Miles of Guideway |  | 0 |  | 0
10.065 | Unspecified | Lineal Miles of Guideway |  | 0 |  | 0
10.070 | Guideway: Underground tunnel | Lineal Miles of Guideway | 5 | 550000 | 50000 | 600000 | 120000
10.071 | Bored Earth Open | Lineal Miles of Guideway |  | 0 |  | 0
10.072 | Bored Earth Close | Lineal Miles of Guideway |  | 0 |  | 0
10.073 | Bored Earth Mixed Shield | Lineal Miles of Guideway |  | 0 |  | 0
10.074 | Bored Earth Mixes Shield SEM | Lineal Miles of Guideway |  | 0 |  | 0
10.075 | Rock Drill & Blast | Lineal Miles of Guideway |  | 0 |  | 0
10.076 | Rock Boring Machine | Lineal Miles of Guideway |  | 0 |  | 0
10.077 | Sunken Tunnel | Lineal Miles of Guideway |  | 0 |  | 0
10.078 | Unspecified | Lineal Miles of Guideway |  | 0 |  | 0
10.080 | Guideway: Retained cut or fill | Lineal Miles of Guideway |  | 0 |  | 0
10.090 | Track: Direct fixation | Track Miles |  | 0 |  | 0
10.100 | Track: Embedded | Track Miles |  | 0 |  | 0
10.110 | Track: Ballasted | Track Miles | 210 | 420000 | 40000 | 460000 | 2190.4762
10.120 | Track: Special (switches, turnouts) | Track Miles |  | 0 | 0 | 0
10.130 | Track: Vibration & Noise Dampening | Track Miles |  | 0 |  | 0
10.140 | Special Structures | Lineal Miles of Guideway |  | 0 | 0 | 0
20 | Stations, Stops, Terminals, Intermodels | Stations | 4 | 131000 | 14000 | 145000 | 36250 | 6.015% | 4.553% | 150075
20.010 | At-Grade Station, Stop, Shelter, Mall, Terminal, Platform | Stations | 3 | 41000 | 5000 | 46000 | 15333.3333
20.020 | Aerial station, stop, shelter, mall, terminal, platform | Stations |  | 0 |  | 0
20.030 | Underground station, stop, shelter, mall, terminal, platform | Stations | 1 | 90000 | 9000 | 99000 | 99000
20.031 | Cut and Cover | Stations |  | 0 |  | 0
20.032 | Bored Earth Soft Soils | Stations |  | 0 |  | 0
20.033 | Bored Rock Hard Soils | Stations |  | 0 |  | 0
20.034 | Unspecified | Stations |  | 0 |  | 0
20.040 | Major stations, landings, terminals: Intermodal, ferry, trolley, etc. | Stations |  | 0 |  | 0
20.050 | Joint development | Stations |  | 0 |  | 0
20.060 | Automobile parking multi-story structure | Spaces |  | 0 |  | 0
20.070 | Elevators, escalators | Number |  | 0 |  | 0
20.071 | Elevators | Number |  | 0 |  | 0
20.072 | Escalators | Number |  | 0 |  | 0
20.073 | Unspecified | Number |  | 0 |  | 0
20.080 | Passenger Overpass | Number |  | 0 |  | 0
20.090 | Underground Interconnecting Tunnel | Number |  | 0 |  | 0
20.091 | Cut and Cover | Number |  | 0 |  | 0
20.092 | Bored Earth Soft Soils | Number |  | 0 |  | 0
20.093 | Bored Rock Hard Soils | Number |  | 0 |  | 0
20.094 | Unspecified | Number |  | 0 |  | 0
20.100 | Signage and Graphics | Number |  | 0 |  | 0
30 | Support Facilities: Yards, Shops, Admin. Bldgs | Number | 2 | 35000 | 7000 | 42000 | 21000 | 1.742% | 1.319% | 43470
30.010 | Administration Building: Office, sales, storage, revenue counting | Number | 1 | 5000 | 1000 | 6000 | 6000
30.011 | Administrative Building | Number |  | 0 | 0 | 0
30.012 | Central Control Facility | Number |  | 0 | 0 | 0
30.013 | Central Revenue Counting Facility | Number |  | 0 | 0 | 0
30.014 | Unspecified | Number |  | 0 | 0 | 0
30.020 | Light Maintenance Facility | Number | 1 | 30000 | 6000 | 36000 | 36000
30.030 | Heavy Maintenance Facility | Number |  | 0 | 0 | 0
30.040 | Storage or Maintenance of Way Building | Number |  | 0 | 0 | 0
30.050 | Yard and Yard Track | Number |  | 0 | 0 | 0
40 | Sitework & Special Conditions | Lineal Miles of Guideway | 105 | 295000 | 31000 | 326000 | 3104.7619 | 13.52% | 10.24% | 337410
40.010 | Demolition, Clearing, Earthwork | Lineal Miles of Guideway | 105 | 25000 | 2000 | 27000 | 257.1429
40.020 | Site Utilities, Utility Relocation | Lineal Miles of Guideway | 105 | 200000 | 20000 | 220000 | 2095.2381
40.021 | Urban Replacement In-Kind Public Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.022 | Urban Replacement In-Kind Private Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.023 | Urban Replacement Betterment Public Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.024 | Urban Replacement Betterment Private Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.025 | Suburban Replacement In-Kind Public Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.026 | Suburban Replacement In-Kind Private Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.027 | Suburban Replacement Betterment Public Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.028 | Suburban Replacement Betterment Private Utilities | Lineal Miles of Guideway |  | 0 | 0 | 0
40.029 | Unspecified | Lineal Miles of Guideway |  | 0 | 0 | 0
40.030 | Haz. mat'l, contam'd soil removal/mitigation, ground water treatments | Lineal Miles of Guideway |  | 0 | 0 | 0
40.031 | HazMat Abatement | Lineal Miles of Guideway |  | 0 | 0 | 0
40.032 | Contaminated Soil Removal | Lineal Miles of Guideway |  | 0 | 0 | 0
40.033 | Ground Water Treatment | Lineal Miles of Guideway |  | 0 | 0 | 0
40.034 | Unspecified | Lineal Miles of Guideway |  | 0 | 0 | 0
40.040 | Environmental mitigation, e.g. wetlands, historic/archeologic, parks | Lineal Miles of Guideway |  | 0 | 0 | 0
40.050 | Site structures including retaining walls, sound walls | Lineal Miles of Guideway |  | 30000 | 3000 | 33000
40.051 | Mechanically Stabilized Earth Walls | Lineal Miles of Guideway |  | 0 | 0 | 0
40.052 | Concrete Walls | Lineal Miles of Guideway |  | 0 | 0 | 0
40.053 | Other Walls | Lineal Miles of Guideway |  | 0 | 0 | 0
40.054 | Unspecified | Lineal Miles of Guideway |  | 0 | 0 | 0
40.060 | Pedestrian / bike access and accommodation, landscaping | Lineal Miles of Guideway |  | 0 | 0 | 0
40.070 | Automobile, bus, van accessways including roads, parking lots | Spaces |  | 0 | 0 | 0
40.071 | Surface Parking Lot | Spaces | 1000 | 10000 | 1000 | 11000 | 11
40.072 | Auto Access | Stations |  | 0 | 0 | 0
40.073 | Bus Access | Spaces |  | 0 | 0 | 0
40.074 | Bus Parking and Berthing | Spaces |  | 0 | 0 | 0
40.075 | Unspecified | Spaces |  | 0 | 0 | 0
40.080 | Temporary Facilities and other indirect costs during construction | Lineal Miles of Guideway |  |  | 0 | 0
40.081 | Roadway Changes | Lineal Miles of Guideway |  | 0 | 0 | 0
40.082 | Third-Party Work | Lineal Miles of Guideway |  | 0 | 0 | 0
40.083 | Mobilization | Lineal Miles of Guideway |  | 0 | 0 | 0
40.084 | Maintenance of Traffic (Railroad reroute, shutdown, reschedule, stage, phase, worker-protect, work-around) | Lineal Miles of Guideway |  | 30000 | 5000 | 35000
40.085 | Unallocated Indirect Costs | Lineal Miles of Guideway |  | 0 | 0 | 0
40.086 | Unspecified | Lineal Miles of Guideway |  | 0 | 0 | 0
50 | Systems | Track Miles | 105 | 216500 | 21030 | 237530 | 2262.1905 | 9.854% | 7.459% | 245844
50.010 | Train control and signals | Track Miles | 105 | 160000 | 16000 | 176000 | 1676.1905
50.011 | Train Control - Wayside | Track Miles |  | 0 | 0 | 0
50.012 | Train Control - On Board Systems | Track Miles |  | 0 | 0 | 0
50.013 | Train Control - Centralized Systems | Track Miles |  | 0 | 0 | 0
50.014 | Unspecified | Track Miles |  | 0 | 0 | 0
50.020 | Traffic signals and crossing protection | Track Miles |  | 20000 | 2000 | 22000
50.030 | Traction power supply: substations | Track Miles |  | 0 | 0 | 0
50.040 | Traction power distribution: catenary and third rail | Track Miles |  | 0 | 0 | 0
50.041 | Catenary | Track Miles |  | 0 | 0 | 0
50.042 | Third Rail | Track Miles |  | 0 | 0 | 0
50.043 | Power Distribution and Connections | Track Miles |  | 0 | 0 | 0
50.044 | Unspecified | Track Miles |  | 0 | 0 | 0
50.050 | Communications | Lineal Miles of Guideway | 105 | 30000 | 3000 | 33000 | 314.2857
50.051 | Wired | Lineal Miles of Guideway |  | 0 | 0 | 0
50.052 | Radio Based | Lineal Miles of Guideway |  | 0 | 0 | 0
50.053 | Unspecified | Lineal Miles of Guideway |  | 0 | 0 | 0
50.060 | Fare collection system and equipment | Stations |  | 500 | 30 | 530
50.061 | Central Revenue Counting Systems | Stations |  | 0 | 0 | 0
50.062 | Revenue Collection - In Station | Stations |  | 0 | 0 | 0
50.063 | Revenue Collection - On Vehicle | Vehicles |  | 0 | 0 | 0
50.064 | Unspecified | Stations |  | 0 | 0 | 0
50.070 | Central Control System | Lineal Miles of Guideway |  | 6000 | 0 | 6000
51 | Construction Subtotal (10-50) | Lineal Miles of Guideway | 105 | 2197500 | 213030 | 2410530 | 78426.4762 | 100% | 75.7% | 2474899
60 | Row, Land, Existing Improvements | Lineal Miles of Guideway |  | 130000 | 13000 | 143000 |  |  | 4.491% | 148005
60.010 | Purchase or lease of real estate | Lineal Miles of Guideway |  | 120000 | 12000 | 132000
60.011 | Full Takes | Lineal Miles of Guideway |  | 0 |  | 0
60.012 | Part Takes | Lineal Miles of Guideway |  | 0 |  | 0
60.013 | Easement Acquisitions | Lineal Miles of Guideway |  | 0 |  | 0
60.014 | Other Rights | Lineal Miles of Guideway |  | 0 |  | 0
60.015 | Donated Value | Lineal Miles of Guideway |  | 0 |  | 0
60.016 | Unspecified | Lineal Miles of Guideway |  | 0 |  | 0
60.020 | Relocation of existing households and businesses | Lineal Miles of Guideway |  | 10000 | 1000 | 11000
60.021 | Residential (Owners) | Lineal Miles of Guideway |  | 0 |  | 0
60.022 | Residential (Tenants) | Lineal Miles of Guideway |  | 0 |  | 0
60.023 | Business (Owners and Tenants) | Lineal Miles of Guideway |  | 0 |  | 0
60.024 | Others (Personal Property Moves) | Lineal Miles of Guideway |  | 0 |  | 0
60.025 | Unspecified | Lineal Miles of Guideway |  | 0 |  | 0
60.030 | Services | Lineal Miles of Guideway |  | 0 | 0 | 0
60.031 | Property Management | Lineal Miles of Guideway |  | 0 |  | 0
60.032 | Agency | Lineal Miles of Guideway |  | 0 |  | 0
60.033 | Contractor R/W Services (Title/Appraisal, etc) | Lineal Miles of Guideway |  | 0 |  | 0
60.034 | Legal Services | Lineal Miles of Guideway |  | 0 |  | 0
60.035 | Unspecified | Lineal Miles of Guideway |  | 0 |  | 0
60.040 | Other Real Estate Costs | Lineal Miles of Guideway |  | 0 | 0 | 0
70 | Vehicles | Vehicles | 15 | 54000 | 7900 | 61900 | 4126.6667 |  | 1.944% | 64067
70.010 | Light Rail | Vehicles
70.011 | Static | Vehicles
70.012 | Articulated | Vehicles
70.013 | Unspecified | Vehicles
70.020 | Heavy Rail | Vehicles
70.021 | Small Scale | Vehicles
70.022 | Large Scale | Vehicles
70.023 | Unspecified | Vehicles
70.030 | Commuter Rail | Vehicles
70.031 | Locomotive | Vehicles
70.032 | Passenger Car | Vehicles
70.033 | Bi-Level Passenger Car | Vehicles
70.034 | Self-Propelled Passenger Car | Vehicles
70.035 | Unspecified | Vehicles
70.040 | Bus | Vehicles
70.041 | Small Bus | Vehicles
70.042 | Standard 40 Foot Bus | Vehicles
70.043 | Articulated Bus | Vehicles
70.044 | Unspecified | Vehicles
70.050 | Other Vehicles | Vehicles
70.060 | Non-revenue vehicles | Vehicles |  | 0 | 0 | 0
70.061 | Maintenance of Way Vehicles | Vehicles |  | 0 | 0 | 0
70.062 | Automobiles | Vehicles |  | 0 | 0 | 0
70.063 | Trucks | Vehicles |  | 0 | 0 | 0
70.064 | Unspecified | Vehicles |  | 0 | 0 | 0
70.070 | Spare parts/ Rotable Components | Vehicles |  | 0 | 0 | 0
70.080 | Intercity Passenger Rail | Vehicles |  | 0 | 0 | 0
70.081 | Diesel Locomotive | Vehicles | 3 | 15000 | 2000 | 17000 | 5666.6667
70.082 | Cab Car | Vehicles | 2 | 9000 | 900 | 9900 | 4950
70.083 | Bi-Level Coach | Vehicles | 10 | 30000 | 5000 | 35000 | 3500
70.084 | Single Level Coach | Vehicles |  | 0 | 0 | 0
70.085 | DMU | Vehicles |  | 0 | 0 | 0
70.086 | EMU | Vehicles |  | 0 | 0 | 0
70.087 | Unspecified |  |  | 0 | 0 | 0
80 | Professional Services |  |  | 385000 | 39000 | 424000 |  |  | 13.31% | 438840
80.000 | Planning and Concept Design |  |  | 30000 | 5000 | 35000
80.010 | Preliminary Engineering |  |  | 60000 | 4000 | 64000
80.020 | Final Design |  |  | 100000 | 10000 | 110000
80.030 | Project Management for Design and Construction |  |  | 100000 | 10000 | 110000
80.031 | Agency Project Management |  |  | 0 | 0 | 0
80.032 | Project Management Oversight Support |  |  | 0 | 0 | 0
80.033 | Agency Force Account |  |  | 0 | 0 | 0
80.034 | Unspecified |  |  | 0 | 0 | 0
80.040 | Construction Administration & Management |  |  | 60000 | 5000 | 65000
80.050 | Professional Liability and other Non-Construction Insurance |  |  | 0 | 0 | 0
80.060 | Legal; Permits; Review Fees by other agencies, cities, etc. |  |  | 15000 | 1000 | 16000
80.070 | Surveys, Testing, Investigation, Inspection |  |  | 15000 | 3000 | 18000
80.080 | Start up |  |  | 5000 | 1000 | 6000
80.081 | Training/Start-up |  |  | 0 | 0 | 0
80.082 | Safety Certification |  |  | 0 | 0 | 0
80.083 | Off-Site Vehicle Testing, Test Runs |  |  | 0 | 0 | 0
80.084 | Commissioning |  |  | 0 | 0 | 0
80.085 | Unspecified |  |  | 0 | 0 | 0
80.090 | Other |  |  | 0 | 0 | 0
81 | Subtotal (10-80) | Lineal Miles of Guideway | 105 | 2766500 | 272930 | 3039430 | 28946.9524 |  | 95.45% | 3145810
90 | Unallocated Contingency | Total Amount |  | 130000 | 15000 | 145000 |  |  | 4.553%
91 | Subtotal (10-90) | Lineal Miles of Guideway | 105 | 2896500 | 287930 | 3184430 | 30327.9048 |  | 100% | 3295885
100 | Finance Charges | Total Amount |  | 0 | 0 | 0 |  |  | 0%
101 | Total Project Costs (10-100) | Lineal Miles of Guideway | 105 | 2896500 | 287930 | 3184430 | 30327.9048 |  | 100% | 3295885
| Allocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  | 9.866%
| Unallocated Contingency as % of Base Yr Dollars w/o Contingency |  |  |  | 5.241%
| Total Contingency as % of Base Yr Dollars w/o Contingency |  |  |  | 15.11%

## Inflation Worksheet
F R A I N F L A T I O N W O R K S H E E T | Issue Date of this worksheet |  |  | 2016-05-04 | Orange cells - Costs prior to the Base Year (2015 in this example). PRODUCTS of the white cells at bottom (inputs) and purple cells (Category-specific compounded inflation factors)
Insert Project Sponsor's Name here | Today's Date |  |  | 2015-06-22 | Green cells - Category-specific annual INFLATION RATES. These are INPUTS. Note that the values shown for these inputs are arbitrary for the purpose of this example.
Insert Project Name and Location | Yr of Base Year $ |  |  | 2015 | Purple cells - Category-specific compounded INFLATION FACTORS. Results of equations using purple and green cells.
Blue cells - Applies category-specific compounded inflation factors in the purple rows … this is for costs beginning in the Base Year (2015)
Insert Current Phase (e.g. Planning, PE, FD, Construction, Rev Ops) | Yr of Revenue Ops |  |  | 2020 | White cells - Base Year costs. These are INPUTS. Values prior to the Base Year are actuals. Values beginning in the Base Year are distributed over time according to the Project Schedule.
Insert comments, notes, etc.
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 100000000 | 100000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 45000000 | 45000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 53350000 | 53250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10250000 | 20000000 | 13000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35175000 | 35175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 20000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77168000 | 77365825.6945 | 0 | 0 | 0 | 0 | 0 | 623090.9688 | 1192518.6006 | 1141166.125 | 2184050 | 5225000 | 50000000 | 10000000 | 5000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 20000000 | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 14581657.3309 | 14581657.3309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555955.9875 | 527500 | 500000 | 527500 | 556512.5 | 587120.6875 | 619412.3253 | 653480.0032 | 689421.4034 | 727339.5806 | 767343.2575 | 809547.1367 | 854072.2292 | 901046.2018 | 950603.7429 | 1002886.9487 | 1058045.7309 | 1116238.2461 | 1177631.3497 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 400274657.3309 | 400372483.0253 | 0 | 0 | 0 | 0 | 0 | 623090.9688 | 1192518.6006 | 1141166.125 | 2740005.9875 | 21177500 | 105500000 | 123527500 | 105556512.5 | 27587120.6875 | 619412.3253 | 653480.0032 | 689421.4034 | 727339.5806 | 767343.2575 | 809547.1367 | 854072.2292 | 901046.2018 | 950603.7429 | 1002886.9487 | 1058045.7309 | 1116238.2461 | 1177631.3497 | 0 | 0 | 0 | 0
Inflation Rate |  |  | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 1.035 | 2.035 | 3.035 | 4.035
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  |  | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01 | 0.01
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  |  | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02 | 0.02
40 SITEWORK & SPECIAL CONDITIONS |  |  | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025 | 0.025
50 SYSTEMS |  |  | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.03
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035
70 VEHICLES (number) |  |  | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04 | 0.04
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045 | 0.045
90 UNALLOCATED CONTINGENCY |  |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
100 FINANCE CHARGES |  |  | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055 | 0.055
Compounded Inflation Factor |  |  | 1.4106 | 1.3629 | 1.3168 | 1.2723 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.0712 | 1.035 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 1.564 | 1.6187 | 1.6753 | 1.734 | 3.5287 | 10.7095 | 43.2128 | 217.5764
10 GUIDEWAY & TRACK ELEMENTS (route miles) |  |  | 1.1046 | 1.0937 | 1.0829 | 1.0721 | 1.0615 | 1.051 | 1.0406 | 1.0303 | 1.0201 | 1.01 | 1 | 1.01 | 1.0201 | 1.0303 | 1.0406 | 1.051 | 1.0615 | 1.0721 | 1.0829 | 1.0937 | 1.1046 | 1.1157 | 1.1268 | 1.1381 | 1.1495 | 1.161 | 1.1726 | 1.1843 | 1.1961 | 1.2081 | 1.2202
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) |  |  | 1.1605 | 1.1434 | 1.1265 | 1.1098 | 1.0934 | 1.0773 | 1.0614 | 1.0457 | 1.0302 | 1.015 | 1 | 1.015 | 1.0302 | 1.0457 | 1.0614 | 1.0773 | 1.0934 | 1.1098 | 1.1265 | 1.1434 | 1.1605 | 1.1779 | 1.1956 | 1.2136 | 1.2318 | 1.2502 | 1.269 | 1.288 | 1.3073 | 1.327 | 1.3469
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS |  |  | 1.219 | 1.1951 | 1.1717 | 1.1487 | 1.1262 | 1.1041 | 1.0824 | 1.0612 | 1.0404 | 1.02 | 1 | 1.02 | 1.0404 | 1.0612 | 1.0824 | 1.1041 | 1.1262 | 1.1487 | 1.1717 | 1.1951 | 1.219 | 1.2434 | 1.2682 | 1.2936 | 1.3195 | 1.3459 | 1.3728 | 1.4002 | 1.4282 | 1.4568 | 1.4859
40 SITEWORK & SPECIAL CONDITIONS |  |  | 1.2801 | 1.2489 | 1.2184 | 1.1887 | 1.1597 | 1.1314 | 1.1038 | 1.0769 | 1.0506 | 1.025 | 1 | 1.025 | 1.0506 | 1.0769 | 1.1038 | 1.1314 | 1.1597 | 1.1887 | 1.2184 | 1.2489 | 1.2801 | 1.3121 | 1.3449 | 1.3785 | 1.413 | 1.4483 | 1.4845 | 1.5216 | 1.5597 | 1.5987 | 1.6386
50 SYSTEMS |  |  | 1.3439 | 1.3048 | 1.2668 | 1.2299 | 1.1941 | 1.1593 | 1.1255 | 1.0927 | 1.0609 | 1.03 | 1 | 1.03 | 1.0609 | 1.0927 | 1.1255 | 1.1593 | 1.1941 | 1.2299 | 1.2668 | 1.3048 | 1.3439 | 1.3842 | 1.4258 | 1.4685 | 1.5126 | 1.558 | 1.6047 | 1.6528 | 1.7024 | 1.7535 | 1.8061
60 ROW, LAND, EXISTING IMPROVEMENTS |  |  | 1.4106 | 1.3629 | 1.3168 | 1.2723 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.0712 | 1.035 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 1.564 | 1.6187 | 1.6753 | 1.734 | 1.7947 | 1.8575 | 1.9225 | 1.9898
70 VEHICLES (number) |  |  | 1.4802 | 1.4233 | 1.3686 | 1.3159 | 1.2653 | 1.2167 | 1.1699 | 1.1249 | 1.0816 | 1.04 | 1 | 1.04 | 1.0816 | 1.1249 | 1.1699 | 1.2167 | 1.2653 | 1.3159 | 1.3686 | 1.4233 | 1.4802 | 1.5395 | 1.601 | 1.6651 | 1.7317 | 1.8009 | 1.873 | 1.9479 | 2.0258 | 2.1068 | 2.1911
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) |  |  | 1.553 | 1.4861 | 1.4221 | 1.3609 | 1.3023 | 1.2462 | 1.1925 | 1.1412 | 1.092 | 1.045 | 1 | 1.045 | 1.092 | 1.1412 | 1.1925 | 1.2462 | 1.3023 | 1.3609 | 1.4221 | 1.4861 | 1.553 | 1.6229 | 1.6959 | 1.7722 | 1.8519 | 1.9353 | 2.0224 | 2.1134 | 2.2085 | 2.3079 | 2.4117
90 UNALLOCATED CONTINGENCY |  |  | 1.6289 | 1.5513 | 1.4775 | 1.4071 | 1.3401 | 1.2763 | 1.2155 | 1.1576 | 1.1025 | 1.05 | 1 | 1.05 | 1.1025 | 1.1576 | 1.2155 | 1.2763 | 1.3401 | 1.4071 | 1.4775 | 1.5513 | 1.6289 | 1.7103 | 1.7959 | 1.8856 | 1.9799 | 2.0789 | 2.1829 | 2.292 | 2.4066 | 2.527 | 2.6533
100 FINANCE CHARGES |  |  | 1.7081 | 1.6191 | 1.5347 | 1.4547 | 1.3788 | 1.307 | 1.2388 | 1.1742 | 1.113 | 1.055 | 1 | 1.055 | 1.113 | 1.1742 | 1.2388 | 1.307 | 1.3788 | 1.4547 | 1.5347 | 1.6191 | 1.7081 | 1.8021 | 1.9012 | 2.0058 | 2.1161 | 2.2325 | 2.3553 | 2.4848 | 2.6215 | 2.7656 | 2.9178
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 101354500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 45450000 | 45904500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 30909033.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10150000 | 10302250 | 10456783.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10302000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5100000 | 5202000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 53831250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 20000000 | 13325000 | 10506250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 31836270 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10300000 | 10609000 | 10927270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 20000000 | 10350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 31824000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15600000 | 16224000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77692457.25 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2000000 | 5000000 | 50000000 | 10450000 | 5460125 | 2282332.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21550625 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5250000 | 5512500 | 5788125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 9499500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499500 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0
Total Project Cost (10 - 100) | 404149636 |  | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2499500 | 20500000 | 105500000 | 126475000 | 110220625 | 29954511 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 0 | 0 | 0 | 0

## Previous Infl. Worksheet
F R A I N F L A T I O N W O R K S H E E T
Insert Project Sponsor's Name here | [7 empty] | Today's Date | 2014-08-28
Insert Project Name and Location | [7 empty] | Yr of Base Year $ | 2014
Insert Project Phase | [7 empty] | Yr of Revenue Ops | 2017
BASE YEAR DOLLARS (X$000) | Base Yr Dollars | Double-Check Total | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 100000000 | 100000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 45000000 | 45000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 53350000 | 53350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 20000000 | 13000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 10000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 35175000 | 35175000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 20000000 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 30000000 | 30000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15000000 | 15000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77168000 | 77167534.0284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593843.1528 | 1147523.0006 | 1108717.875 | 2142450 | 5175000 | 50000000 | 10000000 | 5000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 20000000 | 20000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5000000 | 5000000 | 5000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
#N/A | 7599635.2916 | 7599635.2916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 535076.8875 | 517500 | 500000 | 483091.7874 | 466755.3502 | 450971.3528 | 435721.1138 | 420986.5834 | 406750.3222 | 392995.4803 | 379705.7781 | 366865.4861 | 354459.4069 | 342472.8569 | 330891.6491 | 319702.0765 | 308890.8951 | 298445.3093 | 288352.9559
Total Project Cost (10 - 100) | 393292635.2916 | 393292169.32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 593843.1528 | 1147523.0006 | 1108717.875 | 2677526.8875 | 21217500 | 105500000 | 123483091.7874 | 105466755.3502 | 27450971.3528 | 435721.1138 | 420986.5834 | 406750.3222 | 392995.4803 | 379705.7781 | 366865.4861 | 354459.4069 | 342472.8569 | 330891.6491 | 319702.0765 | 308890.8951 | 298445.3093 | 288352.9559
Inflation Rate |  |  | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035 | 0.035
Compounded Inflation Factor |  |  | 1.6187 | 1.564 | 1.5111 | 1.46 | 1.4106 | 1.3629 | 1.3168 | 1.2723 | 1.2293 | 1.1877 | 1.1475 | 1.1087 | 1.0712 | 1.035 | 1 | 1.035 | 1.0712 | 1.1087 | 1.1475 | 1.1877 | 1.2293 | 1.2723 | 1.3168 | 1.3629 | 1.4106 | 1.46 | 1.5111 | 1.564 | 1.6187 | 1.6753 | 1.734
YEAR OF EXPENDITURE DOLLARS (X$000) | YOE Dollars |  | 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
10 GUIDEWAY & TRACK ELEMENTS (route miles) | 104780125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10000000 | 46575000 | 48205125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20 STATIONS, STOPS, TERMINALS, INTERMODAL (number) | 32149428.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 10712250 | 11087178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30 SUPPORT FACILITIES: YARDS, SHOPS, ADMIN. BLDGS | 10531125 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5175000 | 5356125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
40 SITEWORK & SPECIAL CONDITIONS | 54167250 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10000000 | 20000000 | 13455000 | 10712250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
50 SYSTEMS | 32149428.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10350000 | 10712250 | 11087178.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
60 ROW, LAND, EXISTING IMPROVEMENTS | 35350000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 20000000 | 10350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
70 VEHICLES (number) | 31593375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15525000 | 16068375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
80 PROFESSIONAL SERVICES (applies to Cats. 10-50) | 77423560.75 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2000000 | 5000000 | 50000000 | 10350000 | 5356125 | 2217435.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
90 UNALLOCATED CONTINGENCY | 21074714.375 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000000 | 5175000 | 5356125 | 5543589.375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100 FINANCE CHARGES | 9499500 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 499500 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Total Project Cost (10 - 100) | 408718507.625 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 1000000 | 1000000 | 2499500 | 20500000 | 105500000 | 127805000 | 112978625 | 30435382.625 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000 | 500000
Note on E24: For past years, enter the actual dollars spent in each year. The dollars will inflate when converted to the current base year.
Note on E33: Enter Finance Charges on this line.
Note on O8: Because of inflation, it costs more to buy the same goods and services today than it would have cost in previous years. The total base year dollar cost is a concept that represents the total project cost if the project were planned, designed and built in only one year, the designated base year.
Note on S8: In the white cells, insert project costs in the year in which they occurred (lower rows) or are planned to occur (upper rows) through the completion of the project.
Note on S21: In the Base Year no inflation multiplier is used.